## Tabelle1
| Project | Jupiter`s satellites
| Members of Project | Sophie Scholz, Vittorio Serra, Sebastian Veigl and Michael Lutz
| Number of Task | Task | Performer | Priority | Deadline | Finished | Comment
| 1 | reasearches and inviting orders for a teleskop | Sophie,Michael | High | 2020-11-06 | No
| 2 | inventory of the actual available teleskops and other stuff | all | High | 2020-11-06 | No
| 3 | Translation of Theory of the phenomena of Jupiter`s Galilean satellites | Sophie, Michael | High | 2020-11-06 | No
| 4 | Adding link for Astronomical Algorithm | Vittorio | Medium | 2020-11-06 | No
| 5 | Anaconda user guide | Vittorio, Sebastian | Medium | 2020-11-20 | No
| 6 | Diagram illustrating different methodes (E5,VSOP87...) | Vittorio, Sebastian | Low | 2020-11-20 | No
11 | 7 | Comment software | Vittorio, Sebastian | Medium | 2020-11-06 | No
| 8 | Language decision (German or English) => English | all | Low | 2020-11-06 | Yes
| 9 | High accuracy modell implementation and error correction | all | Medium | 2020-12-20 | No