## Tabelle1
Project | Jupiter`s satellites
Members of Project | Thomas Mannchen, Sophie Scholz, Vittorio Serra, Sebastian Veigl and Michael Lutz
Number of Task | Task | Performer | Priority | Deadline | Percentage of aim reached | Comment
1 | reasearches for a DHBW teleskop | Sophie,Michael | High | 2020-11-13 | 70
13.11.2020: Teleskop already odered waiting for arrival
2 | Translation of Theory of the phenomena of Jupiter`s Galilean satellites | Sophie, Michael | High | 2020-11-13 | 90
13.11.2020: Translation nearly finished (two missing/unclear paragraphs)
3 | Ordering book Astronomical Algorithm (Link for website necessary) | Vittorio | Medium | 2020-11-13 | 30
13.11.2020: library was commisioned to order book, no possibility to order the bock via the William Bell website
4 | Anaconda and Pycharm user guide | Vittorio, Sebastian | High | 2020-11-18 | 50
13.11.2020: Vittoriio nearly finished the Anaconda user guide, Sebastian started the user guide for Pycharm and will finish on the 18.11.2020
5 | Diagram illustrating different methodes (E5,VSOP87...) |  | Low | 2020-11-20 | 0
13.11.2020: no actions until no
6 | Implementing of interpolation of radius values between satellites and jupiter to calculate phenomena | Vittorio, Sebastian | High | 2020-12-04 | 0
13.11.2020: task has been defined and started
7 | Determine deviations from Thuillot`s predictions to evaluate accuracy | Michael | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
8 | High accuracy modell (VSOP87 and E5) implementation | Vittorio,Sebastian | Medium | 2020-12-20 | 90
13.11.2020: calculations are working without softwar error, no tests regarding accuracy have be done
9 | Calculation of sun`s position refering to local place on earth | Sophie | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
10 | Creating astronomical calender including the penomena of Jupiters satellites | Sophie,Michael | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
11 | Implementation of test file test_jupitermoons (necesarry for publication) | Michael | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
12 | Adding functions to main in JupiterMonns.py (examples how to use class JupterMoons) |  | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
13 | Testing the functionality of the calculation method by use of PHÉNOMÈNES DES SATELLITES GALILÉENSDE JUPITER |  | Medium | 2020-12-04 | 0
13.11.2020: task has been defined and started
14
15
16
17
18